| # See, Test & Treat® Program Planning Checklist (It is suggested that programs should be held in April at the Earliest in order to ensure enough time for planning) |  |
| --- | --- |
| # Action | # Notes/Status |
| GENERAL |  |
| Identify priority population |  |
| Finalize location |  |
| Finalize date/dates and timing/timings for the event that works best for community. Consider holidays, weather, etc. |  |
| # Identify a location/locations to hold the program |  |
| Confirm support of your institution/organization to host See, Test & Treat |  |
| Confirm support from the following areas: 1. Hospital/Community Health Center Administration 2. Medical Director 3. Pathologist / Pathology Department 4. OBGYNs 5. Any other Departments that will be involved in screenings 6. Laboratory |  |
| Identify and confirm participation of members of See, Test & Treat Working Group |  |
| Confirm program date with providers and Working Group |  |
| Hold kick-off meeting |  |
| Determine meeting frequency |  |
| Develop template agenda and work plan for Working Group meetings |  |
| Develop contact sheet with names and contact information for Working Group |  |
| Finalize testing services offered (See Supported screenings) |  |
| Confirm screening goal (# patients screened) |  |
| DONORS AND VOLUNTEERS |  |
| Determine funding/items needed |  |
| Determine patient giveaways |  |
| Determine if patient transportation will be provided |  |
| Determine if children’s activities will be provided |  |
| Identify vendors who could possibly provide in kind and financial donations (See Ideas/List of Local Funders to Contact for Support) |  |
| Approach vendors and foundations via email, letters and in person (as appropriate) |  |
| Determine volunteers and roles (e.g. runner, greeters, insurance advocates, etc.) |  |
| Determine if Interpreters are needed |  |
| Determine # of providers needed |  |
| Determine # of volunteers needed |  |
| Recruit volunteers and providers |  |
| Assign volunteers, staff and providers to their positions |  |
| Acknowledge your donors and partners (common practices include acknowledging on flyer, on website, through social media |  |
| Determine how your volunteers will be acknowledged (volunteer certificates are provided) |  |
| SCREENINGS |  |
| Finalize # of appointments that will be offered per service |  |
| Confirm # examination rooms for screenings needed |  |
| Outline registration process to accommodate preregistered patients and walk-ins |  |
| Determine how See, Test & Treat registration and appointments will interface with your EMRs |  |
| Map out how the patients will navigate the program |  |
| Map out how abnormal results will be managed |  |
| Finalize who will oversee follow up care |  |
| Identify program materials needed: banner, signage, etc. |  |
| Determine laboratory services and equipment (mammogram vans) needed |  |
| Coordinate flow for laboratory services needed |  |
| Arrange courier services if needed |  |
| HEALTH EDUCATION |  |
| Determine where health education will primarily take place and who will conduct it. Topics addressed should include: - The importance of the screenings provided and what to expect - The role that pathologists play in these screenings - What an abnormal result means; and - Follow-up steps for abnormal results |  |
| Determine materials that will be utilized for health education |  |
| HEALTH FAIR AND OTHER ACTIVITIES |  |
| Determine what other services you will be offering at your health fair and who would be able to provide those services |  |
| Prepare for Ask-a-Pathologist Table/pathology health education involvement |  |
| Contact Health Fair Vendors |  |
| Confirm food and other activities |  |
| Determine set up needed by Health Fair Vendors |  |
| MARKETING/OUTREACH |  |
| Make a list of organizations and community leaders and businesses that you will conduct outreach through (see Outreach plan (editable template) |  |
| Determine best way to conduct outreach through the identified organizations, community leaders and businesses |  |
| Determine social media plan for Facebook, Twitter, LinkedIn and Instagram |  |
| Determine the best way to conduct INREACH through your existing patient base |  |
| Draft template letter to invite news media, local politicians, community leaders, patient advocates or special guests |  |
| Develop media list: magazines; newspapers, including health reporters and calendar editors; radio; television; Internet; social media outlets; in-house publications, etc. |  |
| Create and send a SAVE THE DATE postcard |  |
| Create and send a FLYER to partners and patients |  |
| Develop media alert for broadcast media |  |
| EXECUTION (1-2 months prior to program) |  |
| Provide CAP Foundation with Hologic request form (at least 6 weeks prior to program) |  |
| Create program materials needed: banner, signage, etc. |  |
| Review 1 month outcomes, 3 month outcomes and 6 month outcomes report and determine data collection plan. |  |
| Review patient program evaluation, patient pre-registration questionnaire, patient liability form and media releases provided on Toolkit and determine whether they need to be modified |  |
| Determine where patient program evaluation, pre-registration questionnaire, patient liability form and media releases will be distributed and collected- look into digitizing the process when possible. |  |
| Put together patient giveaways (Note: CAP Foundation will be providing 100 100 patient giveaways at the beginning of the year) |  |
| Create a floor plan and run of show for day of |  |
| Determine how a “wait list” can be utilized to ensure last minute cancellations do not result in unfilled appointments |  |
| Start marketing and registering patients approximately 1-1.5 months prior to program- OVERBOOK by 15-20% to make-up for no-shows. |  |
| Create Volunteer Schedule |  |
| Call/text patients to remind them about their appointments; send reminder postcards. |  |
| Provide list of organizations and individuals that you would like acknowledged on your “Thank You Banner” to CAP Foundation (3-4 weeks prior to program) |  |
| Order food, supplies needed |  |
| Distribute See, Test & Treat tshirts (limited amount will be distributed at the beginning of the year) |  |
| Schedule volunteer orientation/walk through of program |  |
| Identify and confirm with at least one volunteer and one patient to interview regarding See, Test & Treat experience |  |
| Identify ways to obtain photos during the program (designated photographer? Have all volunteers take photos and upload them to a single site?) |  |
| Share photography shot list with photographers: Photography Shot List. Discuss media releases to seek permission for photographing patients. Discuss ways to identify patients that do not want to be photographed (eg, stickers, beads, bracelets, etc). |  |
| Ensure signage is set up appropriately |  |
| Ensure volunteers/providers/staff know what time and where to check-in |  |
| Let volunteers and staff know that they will be asked for feedback by survey after the program |  |
| Distribute a contact sheet to volunteers and staff for inquiries |  |