|  |
| --- |
| **See, Test & Treat® Program Planning Timeline** |
| **Month 1** | **Action** | **Notes/Status** |
|  | Discuss screening needs of community (breast and cervical cancer screening, etc.) – Identify population at risk |       |
| Discuss market to be served (Hispanic, Chinese, African American, etc.) |       |
| Identify timing for the event that works best for community. Consider holidays, weather, etc. |       |
| Begin to identify possible locations to hold the program |       |
| Confirm support of your institution/organization to host a one- day screening program to provide free cervical and breast screening to underserved women |       |
| Confirm support from the following areas:1. Hospital/Community Health Center Administration2. Medical Director3. Pathologist / Pathology Department4. Gynecologist / Gynecology Department5. Radiologist / Radiology Department6. Laboratory |       |
| Month 2 | **Action** | Notes/Status |
|  | Identify See, Test & Treat Working Group |  |
| Confirm program date with providers and Working Group |  |
| Hold kick-off meeting |  |
| * Determine meeting frequency
* Develop template agenda and work plan for Working Group meetings

Develop contact sheet with names and contact information for Working Group |  |
| Begin to identify testing services offered |  |
| Discuss event logistics – flow of event, timing |  |
| Begin to identify registration process to accommodate preregistered patients and walk-ins |  |
| How will the patients navigate the program |  |
| How will abnormal results be managed [Cervical and Breast] |  |
| Begin to identify vendors who could possibly provide in kind and financial donations, as well as partners (Susan G. Komen for the Cure, American Cancer Society) |  |
| Begin to identify possible education, food, and other activities |  |
| Begin to identify need for interpreters |  |
| Develop a list of supplies needed (e.g. gloves, gauze, etc.) |  |
| **Action** | Notes/Status |
| Month 3 | Discuss Licensing and Credentialing |       |
|  | Discuss Insurance Advocate Position |  |
| Confirm rooms for program |  |
| Finalize list of tests that will be offered |  |
| Finalize the number of vendors needed for health fair |  |
| Begin to identify program materials needed: banner, signage, etc. |  |
|  | Identify number volunteers and roles (e.g. runner, greeters, insurance advocates, etc.) |  |
|  | Continue to contact vendors about supplies |  |
|  | **Action** | Notes/Status |
| Month 4 | Begin to assign people to volunteer positions |  |
|  | Begin to create a floor plan |  |
|  | Draft template letter to invite news media, local politicians, community leaders, patient advocates or special guests |  |
|  | Begin contacting identified health fair vendors, partner, and vendors for in kind donations |  |
|  | Continue to work on program logistics |  |
|  | Begin developing program agenda |  |
|  | Review 1 month outcomes, 3 month outcomes and 6 month outcomes report and determine data collection plan |  |
| Month 5 |  |  |
|  | Develop media list: magazines; newspapers, including health reporters and calendar editors; radio; television; Internet; social media outlets; in-house publications, etc. |  |
| Develop media alert for broadcast media |  |
| Finalize interpreters |  |
| Confirm registration telephone number and process |  |
| Confirm food and other activities |  |
| Confirm partners and in kind donations |  |
| Create and send a SAVE THE DATE postcard |  |
| Month 6 | **Action** | Notes/Status |
|  | Begin to develop See, Test &Treat flyers |  |
| Begin to develop press release for long-lead magazines |  |
| **Month 7** | **Action** | **Notes/Status** |
|  | Finalize See, Test & Treat flyers (approval needed from other sponsors) |  |
| Finalize program signage, banners, etc. |  |
| Distribute press releases to magazine and any publications with a long-lead time |  |
| **Month 8** | **Action** | **Notes/Status** |
|  | Distribute See, Test &Treat flyers at local churches, schools, stores in community; weekend markets, etc. |  |
| Begin scheduling patient visits |  |
| Create volunteer schedule |  |
| **Month 9** | **Action** | **Notes/Status** |
|  | Call patients to remind them about their appointments; send reminder postcards |  |
| Order food |  |
| Distribute press releases |  |
| Provide full volunteer list to CAP Foundation (for certificates of appreciation) |  |
| Schedule day and time to hold a program debrief meeting with all volunteers and the CAP Foundation |  |
| Hold final planning meeting and program walk-through |  |
| **Month 10** | **Action** | **Notes/Status** |
|  | Walk through the program and patient flow with clinical partners and volunteers |  |
| * Confirm patient flow plan with entire team
* Confirm volunteer flow; day of program check-in, roles, assignments, etc.
 |  |
| Confirm education plan and materials are prepared |  |
| Go through pre-program list of supplies and work flow requirements |  |
| Confirm food donations and that food orders are correct and scheduled |  |
| Final confirmation that laboratory services are secured |  |
| * Confirm specimen processing logistics
* If applicable, ensure courier services are scheduled
 |  |
| **Day of Program (before patients arrive)** | **Action** | **Notes/Status** |
|  | Adhere to established patient flow plan |  |
| * Patient registration; patients must fill out registration forms, media release
* Patient waiting areas
* Pelvic and a clinical breast exam
* Educational offerings
* Healthy meal(s)
* Results
 |  |
| **Post Program** | **Action** | **Notes/Status** |
|  | Obtain Volunteer feedback via survey |  |
|  | Submit outcomes data (one month, three month, and six month reports) |  |
| Submit budget reconciliation (one month after program) |  |
| Debrief with volunteers |  |
| Send pictures and stories to CAP Foundation |  |
| Send Thank You cards / emails to volunteers, donors and program partners |  |