2023 SEE, TEST & TREAT STANDARD OPERATING PROCEDURE (SOP) MANUAL

See, Test & Treat Standard Operating Procedure Manual

Table of Contents

- Background: The CAP and the CAP Foundation

- Overview: See, Test & Treat Program

  - Liability

  - Trademark

- Foreword and Purpose of Standard Operating Procedures

  - Cores Requirement of all See, Test & Treat Programs

- Program/Grant Application

  - See, Test & Treat Grant Review Process

    - Funding Schedule/Eligibility

- Steps to Planning a See, Test & Treat

  - Step 1 – Identify a Patient Population

  - Step 2 – Secure a Host Hospital or Clinic with an Underserved Population

  - Step 3 – Identify a Program Coordinator/Recruit a Workgroup to Plan and Implement the Program

  - Step 4 – Estimate Patient Volume

  - Step 5 – Adhere to ACS/ACOG/ACR/ USPSTF Guidelines Screening Guidelines to Determine Patient Eligibility

  - Step 6 – Devise Patient Recruitment Materials

  - Step 7 – Seek Outside Funding

  - Step 8 – Create Pre-registration Process Prior to Patient Recruitment

  - Step 9- Patient Management and Flow

  - Step 10 – Determine Volunteers Needed

  - Step 11 – Create Day-of-Program Registration Process

  - Step 12 – Patient Exam Logistics

  - Step 13 – Patient Education

  - Step 14 – Healthy meals

  - Step 15 – Address Barriers to Care

  - Step 16 – Laboratory, Laboratory Personnel and Specimen Management

  - Step 17 – Deliver Patient Results

  - Step 18 – Follow-up Testing and Treatment

  - Step 19 – Debrief and Celebrate

  - Step 20 – Complete and Report Patient Outcomes and Patient Survey Results

- Rider 1

- Appendices

- Appendix 1: ITEMS ELIGIBLE FOR GRANT FUNDING

- Appendix 2: SAMPLE FLOW- Program, Patient Registration, Screening Mammographies, Pap Test Processing, and Children’s Activities

- Appendix 3: GUIDE FOR DETERMINING VOLUNTEER NEED

# STANDARD OPERATING PROCEDURES FOR SEE, TEST & TREAT, A PROGRAM FUNDED BY THE COLLEGE OF AMERICAN PATHOLOGISTS (CAP) FOUNDATION

## BACKGROUND: THE CAP AND THE CAP FOUNDATION

As the world's largest organization of board-certified pathologists and leading provider of laboratory accreditation and proficiency testing programs, the College of American Pathologists (CAP) serves patients, pathologists, and the public by fostering and advocating excellence in the practice of pathology and laboratory medicine worldwide.

The CAP Foundation, CAP’s 501(c ) (3) philanthropic arm aims to improve people’s health by:

•   Developing tomorrow’s pathology leaders through awards for advanced training, research, and education.

•   obilizing pathologists to expand health equity in medically underserved communities within the U.S. and globally.

Find more information about the CAP Foundation visit www.foundation.cap.org. Contact the CAP Foundation at capfnd@cap.org. Follow the CAP Foundation on

- Facebook at https://www.facebook.com/capfndn

- Twitter at @capfndn.

- Instagram at capfndn.

- Linkedin at https://www.linkedin.com/company/capfndn/about/

## OVERVIEW: SEE, TEST & TREAT PROGRAM

As healthcare evolves, pathologists play a critical role on multidisciplinary teams in the delivery of patient-centered care. See, Test & Treat embodies this leadership as pathologists care for and communicate with their patients. Every See, Test & Treat program begins with a pathologist who recognizes the need in his or her community, champions the program, and rallies a host of partners to deliver patient care.

See, Test & Treat is a free, pathologist-led cancer screening and health education program that brings the power of diagnostic medicine to medically underserved populations with the goals of:

- Addressing health disparities by reducing barriers to care for medically underserved people through health care system partnerships.

- Empowering prevention by delivering dignified cervical and breast cancer screenings—with same-day or prompt results—with a focus on health education.

- Connecting communities by linking patients and their families to a medical home and resources within their own communities.

In a single-day, culturally appropriate program, women receive a pelvic and clinical breast exam, a Pap test with same-day results, a screening mammogram with same-day or prompt results, connection to follow-up care, interpretive services, impactful health education, and translated educational materials to take home.

See, Test & Treat programs are typically a yearly event, often held on a Saturday. Each program reaches between 50 and 150 women and families, making it large enough to deliver real impact and efficiency, yet small enough to ensure a high-quality, dignified experience. The one-day approach effectively addresses barriers encountered by medically underserved women facing health disparities—those who have little to no access to preventative care—and also connects women with a medical home for the future.

## What See, Test & Treat Offers Patients

### Reduced Barriers to Health Care

- Both cervical and breast cancer screenings offered for free to qualifying individuals

- Most programs take place on a Saturday, which enables patient to receive care without taking the day off of work.

- Cervical cancer screening results are provided same day (usually within hours) and breast cancer screening results are provided as soon as possible, reducing the need to make multiple trips.

- If a patient does not have easy access to transportation, many programs provide free transportation through bus passes, ride share gift cards, or round-trip taxi rides.

- If a patient has low English proficiency, an interpreter will be available and, in most cases, bilingual providers and translated health materials are provided.

- To support families, many host sites incorporate children’s activities into the program.

### Increased Health Knowledge and Empowerment

- Preventative screenings and health education services give attendees opportunities to learn about their own health. These opportunities can include an “Ask a Doctor” station, where women have a chance to talk with a pathologist about major contributors to cervical cancer risk, view healthy and cancerous cells through a microscope, and learn about what happens to their Pap test sample in the laboratory.

- Attendees are provided with health education that aims to increase knowledge and change attitudes regarding preventative health care, demystifying the testing process, making patients feel more connected to and comfortable with the health care system.

- Same-day results with direct patient consultations helps relieve anxiety that many medically underserved women feel about medical screenings and procedures.

### Access to Insurance and Follow-Up Care

- Patients are typically connected with financial counselors and patient navigators that help them explore their options for health insurance or affordable health care through local resources.

- Patients with abnormal screening results receive assistance with scheduling their follow-up appointments regardless of the patient’s ability to pay. Many schedule appointments for other health care needs that come to light in their visits—from high blood pressure and diabetes care to behavioral health services and domestic violence support.

## What See, Test & Treat Offers Hosting Institutions

See, Test & Treat establishes your institution as a safe and welcoming environment where community members can receive health care and understand what resources are available to them.

Ten years of events at a variety of institutions across the US shows that See, Test & Treat helps establish institutions as a community information hub that offers families a safe place to explore their health care options. Furthermore, hosting a See, Test & Treat program also fulfills community event obligations often required for hospitals and cancer care centers by accrediting organizations.

## What See, Test & Treat Offers an Institution’s Employees, Clinicians, and Medical Students

This highly collaborative event has proven to enhance interdepartmental and employee relationships by acting as an effective team building exercise. See, Test & Treat also offers a valuable teaching experience to residents and medical students who appreciate the opportunity to interact with the public and patients while experiencing different sides of the health care system. Past medical student and resident volunteers have reported being able to assist with procedures that would have been otherwise unavailable to them and gaining valuable insight into patient care and public health issues.

See, Test & Treat Grant Funding

Funding is open to CAP members in partnership with a 501(c)3 non-profit organization(s) to support programs taking place in the US. Note, award funding will only be made to a 501(c)3 organization. Also note that grant funding is not guaranteed and should not be considered ongoing.

Applicants must have the following in place before applying for a grant:

- Ability to screen at least 50 women per program

- Ability to support the four core program components: Free cervical and breast cancer screenings for uninsured or underinsured women;Same-day results for cervical cancer screenings; results same-day (preferable) or within one week for breast cancer screenings; Culturally, linguistically appropriate health education for your target communities; Connection to care for any individual in need of follow-up services or treatment, regardless of health insurance status)

- A committed pathologist leader who is also a member of the CAP. The pathologist leader must be part of the on-site health care team providing services at the See, Test & Treat program.

All applicants will be considered regardless of age, race, gender, or national origin

##### Liability

The CAP Foundation assumes no, and hereby disclaims all, liability for the testing, diagnosis, or treatment of women participating in the See, Test & Treat program (see Rider 1). Participating sites should engage their Compliance and/or Risk Management Department to gain an understanding of and address any liability issues. It is expected that the care, testing, and treatment to be provided in the See, Test & Treat protocol by the participating gynecologists, cytologists, radiologists, pathologists, and mammography technologist shall be consistent with the standards of care applicable to such specialties.

##### Trademark

See, Test & Treat® is a registered trademark of the CAP Foundation. Prior to public use of the name and trademark, permission must be granted by the CAP Foundation. All intellectual property relating to See, Test & Treat® is owned exclusively by the CAP Foundation and shall remain the sole property of that party unless otherwise agreed in writing. Intellectual property arising out of collaborative activities will be determined in definitive agreements.

##### Important COVID-19 Requirement:

All users of this See, Test & Treat procedures manual acknowledge that local, state, and federal regulations and guidance apply to Covid-19 health and safety measures and may be modified at any time by such government entities. Accordingly, at all times when using this See, Test & Treat standard operations manual, all persons must comply with all local, state, and federal regulations and guidance relating to covid-19 health and safety. This includes but is not limited to modifying adherence to this See, Test & Treat standard operations manual in such a manner as to fully comply with the current iterations of such regulations and guidance.

### FOREWORD AND PURPOSE OF STANDARD OPERATING PROCEDURES

The CAP Foundation’s See, Test & Treat Standard Operating Procedures (SOPs) provide direction to individuals and organizations involved in the planning and execution of a See, Test & Treat program. This document is not intended to address all possible variations that may arise in the planning and execution of See, Test & Treat programs. More detailed and specific resources are available to complement these SOPs in the appendices, or by contacting the CAP Foundation at capfdn@cap.org. Additional resources are available in the  See, Test & Treat Toolkit for grantees, who will be given access to the folder upon request.

This SOP Manual is intended to be a living document that may be adapted when needed, but it may not be altered without the approval of the CAP Foundation staff.

The purpose of the SOPs are as follows:

- Provide a baseline standard for planning, execution and follow-up that is applicable to any See, Test & Treat program.

- Ensure all participants focus on their specific tasks while being knowledgeable of all other areas to ensure a smooth and successful program.

- Create continuity around the knowledge of how See, Test & Treat programs are intended to function.

- Ensure a consistent quality experience for patients, clinicians, volunteers, health care systems, and the community.

- Offer guidance and approaches to ensure repeatable and scalable programs. These SOPs apply to all See, Test & Treat programs.

##### Core Program and Grant Requirements

- CAP member pathologist to lead or co-lead a program to offer cervical and breast cancer screening to a U.S. community of medically underserved (uninsured or underinsured) women.

- The CAP member pathologist will partner with a volunteer, multidisciplinary clinical team and host site for care of patients.

- A hospital/clinic program host with the capacity to provide a Pelvic and Clinical Breast Exam, Pap test, and Screening Mammogram to eligible women.

- Preference is given to 501(c)3 organizations to act as recipient and fiduciary of CAP Foundation grant funding.

- Provision of same-day Pap test results and same-day or prompt Screening Mammogram results (within one week).

- Same-day results delivered face to face or over the phone.

- Establishment of a best practices protocol for delivering patient results that cannot be conveyed the same day. This may involve a phone call and certified letter to make sure patients are not lost to follow-up.

- Provision of available information about financial aid, charity programs, state or federal assistance, and health insurance marketplace exchange.

- Adherence to the American Cancer Society (ACS), American College of Radiology, the American Congress of Obstetricians and Gynecologists (ACOG) and/ or the US Preventative Services Task Force Guidelines.

- Conformance with acceptable standards of practice for the screening and diagnosis of cervical and breast cancer.

- Compliance with appropriate federal, state, and local health provider licensing and regulations for cervical and breast cancer screening.

- Connection to follow-up care for patients with abnormal results.

- Culturally sensitive, translated, patient-centered education and health information.

- Submission of a completion of Patient Outcomes Data Form within 1 month, 3months and 6 months post program.

Program/Grant Application

To take this life-saving program to the next level, the CAP Foundation has established an 18-month program pipeline. An aid to host sites as well as Foundation operations, our 18-month program pipeline ensures advanced planning; budgeting and fundraising—all vital areas needed to help See, Test & Treat achieve greater scale and impact.

The CAP Foundation offers See, Test & Treat grants of up to $20,000 to support See, Test & Treat program expenses that other grants and in-kind donations do not cover. This grant typically pays for items such as exam and laboratory supplies, equipment rental, promotional materials, educational aids, interpreters, translation of materials, patient transportation, and meals.  Note that the grant application process is competitive- grant funding is not guaranteed and should not be considered ongoing.

The CAP Foundation encourages volunteerism whenever feasible and supports See, Test & Treat programs by procuring in-kind donations of testing kits and supplies, loaner equipment whenever possible, as well as knowledge sharing in terms of running effective programs. Please see Appendix 1 for a description of items eligible for funding. Note that patient incentives should amount to no more than $10/patient.

As See, Test & Treat continues to expand, we look to programs to become more self-sustaining and actively pursue other sources of funding in addition to securing in-kind donations in the areas of refreshments/food, supplies, promotion and publicity.

Our program process begins with our Request for Applications (RFA), each summer - for programs targeting delivery in following year.

Pathologists and institutions interested in hosting a program and applying for CAP Foundation See, Test & Treat grant funding must complete and submit a grant application, which can be found on the CAP Foundation Grants and Awards Application Site :

See, Test & Treat Grant Review Process

The CAP Foundation Grants Committee will review all applications and award funds on behalf of the CAP Foundation Board of Directors.

Programs are evaluated on the need for the program in their target area, as well as their ability to:

- Identify medically at-risk (uninsured/underinsured) population facing barriers to care

- Reduce barriers to cervical and breast cancer screening and follow-up care

- Advance early detection and treatment of cervical and breast cancers

- Provide measurable results and outcomes

- Utilize standardized procedures set forth by the CAP Foundation

- Garner local financial and in-kind support to increase the financial sustainability of the See, Test & Treat program

Furthermore, repeat applicants are evaluated on their performance in previous years.

Awards Disbursement

The grant recipient will receive 50% of the award upon official approval of the application by the CAP Foundation Grants Committee no later than 6 weeks prior to the program date and the remaining 50% will be awarded 6 weeks after a program outcomes report, a budget reconciliation form and supporting receipts have been turned in. Each program is required to submit the See, Test & Treat outcomes data worksheet no later than 30 days following the program along with documented program costs to receive the balance of the funds. This aggregate program data will be used to develop a formal research protocol to track and monitor the impact of See, Test & Treat and to improve the program design.

The CAP Foundation will not provide See, Test & Treat grants to the following entities:

- Individuals

- Social organizations

- Trade or business associations

- Memorials, such as cultural exchange programs or program to benefit any particular individual, including individual travel and/ or study

All organizations applying for See, Test & Treat program grants from the CAP Foundation must demonstrate solid financial and program management.

## STEPS TO PLANNING A SEE, TEST & TREAT  PROGRAM

Step 1: Identify a Patient Population

See, Test & Treat serves women residing in medically underserved populations (MUPs) OR patients who live in medically underserved areas (MUAs)”

•	MUPs have a shortage of primary care health services for a specific population subset within an established geographic area. These groups may face economic, cultural, or linguistic barriers to health care.

•	MUAs are areas that have a shortage of primary care health services for residents within a geographic area as established by the Health Resources and Services Administration (HRSA) through the following website: https://data.hrsa.gov/tools/shortage-area/mua-find

Specifically, programs should focus on recruiting women who are medical underserved or live in MUAs and who are in need of breast and cervical cancer screenings in accordance with established guidelines (e.g., ACR, ACS, USPSTF or ACOG) .

### Resources for identifying local patient population with limited access to health care and low breast and cervical cancer screening rates:

- Your local/county public health department

- State public health departments

- Your hospital’s community outreach/population health department

- US Census data

- HRSA website: https://data.hrsa.gov/tools/shortage-area/mua-find

- Centers for Disease Control and Prevention

- National Cancer Institute (NCI) Fact sheet

Step 2: Secure a Host Hospital or Clinic with a Medically Underserved (Uninsured and Underinsured) Population

- Confirm support of the host site institution/organization and commitment from the following areas:

    - Hospital/Clinic administration

    - Medical director

    - Pathology department/chair

    - Gynecologist/gynecology department

    - Radiologist/radiology department

    - Cytology Laboratory director/chair

    - Marketing/Communications/Public Relations department(s)

    - Patient advocate/community outreach

    - Interpreter Services

    - Registration

    - Financial aid department

    - Community Outreach department (if available)

    - Health insurance marketplace provider (to provide enrollment information)

    - Facility Department (security, event set-up, parking/traffic control)

    - Schedule a program date approved by the host organization and the CAP Foundation.

- Avoid scheduling programs that conflict with hospital, community events or holidays.

    - Consider factors that could be impacted by weather, especially if any part of the program will be held outdoors

    - Consider whether the program would be more successful held as multiple smaller events or one larger program

    - Confirm the availability of any vital community partners needed to support screenings (e.g., mobile mammography vans, supporting external laboratories)

    - Consider sufficient space for patients, accompanying family members or friends, clinical services, education and food.

    - Confirm with institution/organization that event space and exam rooms are available.

    - Confirm where and how host site will connect patients to follow-up care and treatment when abnormal or cancer results are discovered

    - Confirm that transportation to your program is available.

### Step 3 Identify a Program Coordinator and Recruit a Workgroup to Plan and Implement the Program (See Toolkit for a Workplan Template)

It is recommended that all See, Test & Treat programs identify a program coordinator to assist with planning/organizing/coordinating all program logistics such as scheduling planning group meetings, taking meeting minutes, and coordination of follow-up assignments; ideally this person has project management skills. Consider reaching out to a part-time staff person or a retired clinician who may be interested in taking on a temporary assignment; those in administrative fellowships or graduate students may value the experience in serving as a program coordinator.

For optimal outcomes, your workgroup should consist of a combination of the following:

- Program Coordinator/Organizer

- Pathologists

- Cytotechnologists

- Gynecologists

- Oncologists

- Nurses

- Radiologists

- Mammography Technicians

- Registration

- Financial aid/insurance marketplace navigators

- Public Relations, Marketing or Communications Representative

- Administrative staff

- Patient advocates

- Community outreach

- Interpreters (any interpreters involved in translation of test results, medical procedures, follow-up care, etc. must be medically certified)

- Building/Facilities representation

### Step 4: Estimate Patient Volume

Use the following planning guidelines to estimate number of patients:

- Establish the number of private examination rooms available for screening.

- Determine the number of clinicians available to provide patient exams and screenings.

  - Estimate the amount of time needed for patients to change into a hospital gown.

  - Allow ample time for a pelvic and Clinical Breast Exam, Pap test, patient, and clinician questions (15 to 20 minutes).

  - Estimate the time for patients to dress after exams.

  - Determine the amount of time necessary to transition from exam room to mammography.

  - Determine the amount of time for patients to undress.

  - Determine time needed to perform Screening Mammograms (20 minutes).

  - Use the above information to estimate the number of women who can be served.

  - Determine whether your cytology will be done on-site or at another location.

  - Determine your method of offering mammography screenings (i.e., within your institution, on a mobile coach or at an off-site location)

  - Estimate the amount of time needed to process, read, interpret, and deliver results.

  - Set the program hours of operation to achieve goals.

  - IMPORTANT : Think about your typical clinic no show rate and consider registering additional patients to mitigate this (or create a patient wait-list)

Step 5: Adhere to ACS, ACOG, ACR or US Preventative Services Task Force Guidelines to Determine Eligibility

| Organization | Website |
| --- | --- |
| American Cancer Society | Cervical : http://www.cancer.org/health-care-professionals/american-cancer-society-prevention-early-detection-guidelines/cervical-cancer-screening-guidelines.html Breast: https://www.cancer.org/cancer/breast-cancer/screening-tests-and-early-detection/american-cancer-society-recommendations-for-the-early-detection-of-breast-cancer.html |
| American College of Obstetrics and Gynecology | Cervical: https://www.acog.org/Clinical-Guidance-and-Publications/Practice-Advisories/Practice-Advisory-Cervical-Cancer-Screening-Update Breast: https://www.acog.org/clinical/clinical-guidance/practice-bulletin/articles/2017/07/breast-cancer-risk-assessment-and-screening-in-average-risk-women |
| American College of Radiology | Breast: https://www.acraccreditation.org/mammography-saves-lives/guidelines |
| US Preventative Services Task Force Guidelines | Cervical: https://www.uspreventiveservicestaskforce.org/uspstf/recommendation/cervical-cancer-screening Breast: https://www.uspreventiveservicestaskforce.org/uspstf/recommendation/breast-cancer-screening |

### Step 6: Devise Patient Recruitment Materials

- Create Media and Marketing Plan (see See, Test & Treat Toolkit)

- Engage marketing, communications and/or public relations personnel at the beginning of the planning stages to develop a program outreach and/or promotional strategy. Programs should focus on conducting outreach to patients that are not connected with your health care institution already and do not have a medical home

- Please do not abbreviate “See, Test & Treat”- use the full name in all your marketing materials

- Ensure that you have  language appropriate marketing materials for your target populations.

- Distributing information via word of mouth is still an effective tactic as majority of people still receive information in this manner. Engage community leaders (faith leaders, governmental officials, school officials, friends and family) and community stakeholders (small business owners and employees, librarians, local health care systems) and ensure that that these people/organizations are aware of your program and can promote See, Test & Treat on your behalf.

- Distribute promotion/patient recruitment materials a minimum of 6 weeks in advance of the program date (templates found in See, Test & Treat Toolkit)

- Work with community outreach experts within your institution and/or within the community to reach target populations.

- Provide/include talking points for consistent messaging by outreach personnel or if material is provided as a leave behind.

- Employ community advocates to visit and recruit patients from the community or local to the area.

- Post multilingual flyers in locations frequented by the target audience such: as beauty salons, women’s shelters, churches, libraries, community centers, grocery and other stores, laundromats, ESL classes, local workplaces, fast food restaurants, and currency exchanges.

- Post multilingual flyers in your clinic or hospital.

- Cross promote your See, Test & Treat program at other community events; look for speaking engagements.

- Consider use of social media including Event Brite sign-up portal, Constant Contact to gather names and generate email notifications.

- Contact local radio to conduct free public service announcements; community calendar announcements.

- Contact local cable TV hosts to interview members of the planning team.

- Advertise in newspapers; community calendars.

- Post on hospital website, Facebook, and Twitter. (See Facebook/Twitter Instructions in the Media Kit)

- Create tactics to remind patients of their appointment times and any last-minute instructions (mitigate no show rate).

  - Reminder Phone Calls

  - Text Messages

  - Postcards

  - Magnet (with appointment information)

Conduct pre-program workshops for resistant populations that may require additional information before participating.

  - Create cultural awareness and sensitivity by holding a simple event to explain to women and their families what happens at a See, Test & Treat program.

  - Have interpreters, volunteers, and clinicians available to field questions.

  - Familiarize community influencers with the program and key messages about the importance of cervical and breast cancer screenings.

  - Include diagrams and education about the procedures that will take place during the program.

### Step 7: Seek Outside Funding

To work towards achieving sustainability, sites are encouraged to seek in-kind and local financial donations. Keep in mind that not everyone you ask to donate knows about your See, Test & Treat program. Clearly state why you are seeking donations, what the current situation is and what the desired outcome will be.

Identifying additional funding opportunities

Seek local funding opportunities, donations and partnerships (Explore See, Test & Treat Toolkit for ideas). Get in touch with your program manager for help, guidance, and suggestions as to how to approach funders.

- Research local foundations, local businesses, community groups (i.e. Exchange Clubs, Rotary clubs, women’s clubs, etc.) and institutions that would be interested in providing funding to local programs. Be mindful of grant application deadlines and funding cycles.

- Connect with businesses and organizations in the community who might be interested in donating food, transportation, or items for the program. Additionally, utilize these connections as a means to promote the program and recruit participants.

- Work with your institution’s grant writer or outreach staff to identify key community groups or businesses that have a relationship with your institution.

- Talk with board members and key stakeholders at your institution to determine if they are connected with any organizations, clubs or businesses that would be interested in supporting See, Test & Treat.

Simple tips to follow when reaching out and asking for a donation (See , Test & Treat Toolkit for template)

- Use simple and direct language: Be clear on the goals of the program, the number of people it will benefit and who will be at the program. Consider telling a story to explain your See, Test & Treat program, its impact on the community and why you are asking for a donation. If you have hosted a See, Test & Treat program before, use patient stories of patients from  past programs to illustrate the impact on the women serve through the event..

- Do tailor your message: Determine how you will make “the ask” (phone call, casual email note or formal letter); think about appealing to each person’s individual or business interests to make a correlation with See, Test & Treat.

- Do know what you’re asking for: It’s important to clearly outline your request.

- Do know who you’re asking: Make sure you know who your audience is when you ask for donations.

- Don’t be scared of rejection: You will not get a donation from every person you ask, and that’s okay.

- Do have a positive attitude: Stay positive, let people know the impact their donations will have on the success of your See, Test & Treat program and why it’s important.

- Do think outside the box: Get creative when you ask for donations for your See, Test & Treat program, and experiment with connecting with others via email, social media, in person, or better still, all three!

### Step 8: Create Pre-registration Process Prior to Patient Recruitment (See , Test & Treat Toolkit for guidance)

- Work with your Billing/Finance department to set-up a special code/guarantor account to use for See, Test & Treat patients so they will not receive a bill for screening services provided at the event. Make sure this account code is shared will all relevant departments. This is a way to mark your See, Test & Treat participants so that you are able to easily run reports on them for data/outcomes reporting.

- Determine whether registration will be conducted by phone, or online.

- Devise a prescreening form to gather patient contact information, demographic information, health insurance status patient/family history for cervical or breast cancer, and eligibility for screening based on age and ACOG/ACS/ACR/USPSTF screening guidelines. Ensure that the forms collect data that needs to be reported to the CAP Foundation.   Have the patients indicate if they need an interpreter during the program.

- Create a script in which to train registration staff so all are asking potential patients the same questions as well as giving correct event details. In addition, staff needs to understand and answer questions regarding the circumstances under which a patient would or would not receive a Pap test or Screening Mammogram.

### Begin a patient tracking spreadsheet to keep track of # of patients being registered. (See , Test & Treat Toolkit for guidance)

- Permit registration staff to access appropriate databases to look up dates of previous screenings (Pap and/or Screening Mammogram) to confirm eligibility.

- Advise patients that the name on their photo ID should be the name used when pre-registering and completing all forms for See, Test & Treat and future medical visits. Include this information and procedures in patient outreach and recruitment activities.

- Mitigate the patient no-show rate – overbook or double book appointments based on your institution’s typical no-show rate.

- Utilize a waitlist, with a plan to contact women for unfilled appointments. These women can still attend educational segments.

- Plan to accommodate walk-ins to fill appointment slots made available by women who do not keep their appointments, aka no-shows.

- Plan for interpreters to meet population needs (any interpreters involved in translation of test results, medical procedures, follow-up care, etc. must be medically certified).

- Assign volunteers to place reminder phone calls/text messages to registered participants two to three days prior to event to confirm appointments.

### Step 9: Patient Management and Flow

- Map out your See, Test & Treat program to determine the best use of available space, patient flow and interaction among departments. Create workflows (See examples of these flows in Appendix 2 ) for your program, patient registration (pre-registration and on-site registration) mammography, pap test processing  and children’s activities

- Determine location of check-in areas for patients and volunteers.

- Determine location for on-site registration of See, Test & Treat patients.

- Ensure patient forms are completed and collected during the on-site registration process, including:

  - Host site registration forms.

  - Patient consent to health screening and waiver of liability (see See, Test & Treat Toolkit)

  - HIPAA compliance and patients to be offered the opportunity to receive a copy of the “Notice of Privacy Practices.”

  - CAP Foundation media release form (see See, Test & Treat Toolkit)

  - For patients who do not wish to be photographed, establish a visible way to identify them to the photographer (e.g., no photo sticker, colored beads, etc.).

- Consider having patients go to a check-in station either before or after on-site registration; use this station to orient patients to the program. This area can provide additional information/handouts such as their appointment times, a program map to help patients find various program locations, health ticket/activity card so patients know what is happening throughout the day (have patients check off each activity as an incentive to participate and complete their card.) Volunteers can view patient health ticket/activity card to help direct individuals throughout the program. (Sample in See, Test & Treat Toolkit)

- Determine need for interpreters or patient escort; assign as needed to help guide  patient to screening appointments and/or activities to assure timeliness and engagement.

- Show patients where the restrooms and refreshments are kept.

- Station volunteers in corridors and main areas to help guide patients and answer questions. Consider providing patient guides/interpreters and/or station volunteers throughout the main program areas to assist patients with questions or to help them determine where they should go next (Note: Interpreters should be clearly marked so that patients can recognize them when needed. A badge indicating the language they speak is a good way to make them recognizable as interpreters)

- Consider color coding key areas using balloons and/or signage.

- Ensure appropriate signage throughout site to guide the women to registration, screening, education, and check-out areas. Create multilingual signage as needed  to support your patient audience.

- Determine location of check-out areas for patients and volunteers.

- Ensure volunteers are available to See, Test & Treat patients to answer questions or collect any forms prior to leaving event.

- Determine with your planning team how patients with abnormal results will be connected with the additional screenings and care that are needed, ensuring that medically underserved patients are connected with affordable care.

Step 10: Determine Volunteers Needed

Create a contact sheet for all volunteers to include their full name, role, responsibility, and contact information (phone/email). All volunteers should be familiar with HIPAA Guidelines specific to patient Protected Health Information (PHI).

Using the information to estimate the number of patients to be screened in Step 5, determine the number of volunteers and clinicians (who are licensed, credentialed, or granted privileges) to provide services at the program. While program planning, also consider the role of pathologists- the See, Test & Treat Toolkit has a document summarizing possible roles filled by residents, fellows and attending pathologists.

(See Appendix 3 – Guide for Determining Volunteer Need).

These are some positions that will need to be filled by volunteers:

Program Logistical Support:

  - Program Coordinator

  - Volunteer Coordinator

  - Education Coordinator

  - Health Fair Coordinator

  - Children’s Activity Coordinator

  - Food Coordinator

  - Greeters

  - Interpreters (medically certified)

  - Additional Interpreters (not medically certified)

  - Patient Escorts

  - Specimen Couriers

  - Exam Room Attendants

  - “Float” volunteers

  - Photographer

  - Security

  - Parking Attendants

  - Check-In Station (patients and volunteers)

  - Onsite Patient Registration

  - Patient Navigators

  - Check-Out Station (patients and volunteers)

Patient Screening Support

- Conduct pelvic and Clinical breast exams

- Perform Pap test

- Process and read Pap specimens

- Perform Screening Mammogram

- Read and interpret Screening Mammograms

- Discuss results with patien

Here are some best practices for Volunteer Recruitment and Volunteer Management

- Begin volunteer recruitment early within your own specialty

- Advertise in institutional newsletter, website, bulletin

- Enlist other specialties and community advocates to announce opportunity in staff and group meetings

- Circulate/post a volunteer announcement and sign-up sheet, website, etc.

- Create a volunteer contact sheet to include: name, contact information, role, responsibility, and time commitment; circulate among volunteers.

- Create job descriptions and expectations for each volunteer role (See See, Test & Treat Toolkit)

- Develop a process/procedure for each area so volunteers understand what is happening and what they need to do.

### Volunteer Orientation (See See, Test & Treat Toolkit)

### Define the expectations of your volunteer team; provide a written orientation packet if needed to include event logistics (volunteer roles, dress code, start/stop times, patient screening, education and food areas, volunteer areas, key contacts), along with any last minute instructions

- Develop a program map so volunteers can familiarize themselves with the activities and locations throughout the building so they will know where to find things and what is happening at various times throughout the day.

- Assign key leaders to manage each volunteer group.

- Make sure all volunteers are wearing their See, Test & Treat t-shirt and name tags;

- Schedule a walk through the day before your See, Test & Treat event to allow volunteers to become oriented with the program and ask questions.

- Hold a 5 to 10-minute huddle the day of your See, Test & Treat program to orient volunteers and to answer any last minute questions. Conduct a walk-thru with volunteers if time allows.

- Make sure volunteers know what is happening in their area specific to patient and clinician interactions.

- Share key documents (e.g. patient registration lists, volunteer contact sheet), program map, pager numbers, phone and fax numbers with volunteers as feasible.

- Consider appointing someone to monitor and manage volunteer staffing at each station/location throughout the day of the event. This will prevent understaffing and volunteers not having the opportunity to take a break or get food. Make sure food is available to all volunteers throughout your See, Test & Treat program.

### Confirm volunteer role, responsibility and hours of participation.

### Remind volunteers to check-in and check-out when arriving/departing the program.

### Instruct volunteers to communicate with their colleagues – share information about what is happening during the day.

### Discussing patient information or programmatic issues in public spaces is never a good idea; remind volunteers to seek out assistance and a private area to discuss and get guidance.

- Remind volunteers that they could be asked to pitch in as needed and may be asked to do something outside of their assigned role.

### Step 11: Create Day-of-Program Registration Process (Also See Step 9: Patient Management and Flow)

- Utilize electronic health records whenever possible to accurately capture patient contact information, demographic information, screening eligibility, patient/family history for cervical or breast cancer, and follow-up information.

- Work with all departments to consolidate the gathering of patient information (avoid the need for patients to provide duplicate information at different stations).

- Verify information gathered from preregistered patients. Reminder: patients should use the same name that is on their photo ID.

- Have patients communicate how they would like to be contacted. This may include postcard, phone call/text, email, or mail.

- Have the patients indicate if they need an interpreter during the program. If they do, then connect them with one or let them know how to identify an interpreter at the program (interpreters that are walking around the health fair should be clearly marked with a nametag indicating what language they speak).

- Have patients complete registration forms, HIPAA forms, media releases and waivers, as necessary.

- Create a program agenda listing locations and times of other activities, education and screenings taking place during your See, Test & Treat program that women can participate in while waiting for test results. Provide this information as a handout or poster or both. Orient volunteers prior to the event; make sure to explain this to patients when they are checking in.

- Provide a pre-made folder with all patient documents needed for program participation will need for participating in the program, including an activity card so patients can check off when they complete an activity or receive a screening, appointment times, media releases, and patient evaluations.

- Remind women of the importance to remain at the program to get results and complete a post-program questionnaire (utilize an incentive if needed).

- If a paper-based patient registration system is used, ensure there are multiple copies so that gynecology, mammography, and the laboratory have necessary information for initial testing and follow-up procedures.

- Have a system for ensuring that patient contact information has been captured, should paper forms be lost or misplaced.

- Have a system in place for efficiently locating patients when their results are ready- consider using a restaurant paging type device.

### Patient Identification

- Develop a patient identification system so that results can be readily and correctly matched.

- Follow all HIPAA guidelines specific to patient Protected Health Information (PHI).

### Waiting Area

- Choose an area for patients to wait for screening and/or results.

- Determine what other activities will be available for patients to participate in while they are waiting.

- Keep the patients engaged and informed to foster a more meaningful, long-term clinical relationship with health care providers.

### Step 12: Patient Exam Logistics

### Develop a rotation system to utilize multiple patient exam rooms & providers.

### Assign individuals to specific exam rooms to ensure efficient room turnover for next patient exam.

### Please make sure all rooms are outfitted with equipment needed to complete patient exams (i.e.: sufficient lighting).

### Note: Advise providers against excessive use of lubricant during Pap tests to avoid compromising of specimens

### Step 13: Patient Education

The time between cervical and breast cancer screenings and waiting for same-day test results provides a perfect window of opportunity to engage women and their families in education. See, Test & Treat leverages this wait time to persuade women to take control of their health and encourage family and members of the community to do the same. The most important factor is that education and educational materials are translated and culturally appropriate.

The CAP Foundation has developed patient education materials for use at See, Test & Treat programs. Other organizations, such as the CDC and American Cancer Society also provide educational materials. These educational materials can be found in our online See, Test & Treat Toolkit. Ideally these materials would be handed to your patients at check-in or registration or at a health education table so that a health professional can walk them through the information and answer any questions

### Educational topics that should be covered throughout your program are:

### Importance of receiving pap tests and mammograms regularly

### Where patients can get their preventative screenings (a list of local clinics or FQHCs that they can go to)

### What happens after they get their pap test (Ask a Pathologist table)

### Ideas for education include:

- Education through games at the health fair (incorporate health facts into games such as Wheel of Fortune, Jeopardy and Bingo)

- Health Education done by providers during medical appointments.

- Health education conducted while patients are in waiting room.

- Ask a Doctor/ Pathologist table- where patients can look through a microscope to see what normal vs. cancerous cells look like. Patients interact with pathologists and other physicians along with having the opportunity to  ask them questions- this is a good way to demystify the process of what happens after you get your pap test and mammogram.

- Health fair featuring vendors and community resources that your target population could benefit from

- Demonstration of self-breast exams and disease states with interactive anatomic models or posters

- Looping videos or slide shows with educational content in waiting areas (A playlist is provided on the See, Test & Treat Toolkit under “Education Materials”)

### Patient Program Evaluations: (See See, Test & Treat Toolkit)

### In addition to a See, Test & Treat Activity Checklist, programs should provide patient evaluation forms and story cards to gather information about patient experience, knowledge/attitude changes and satisfaction.

- Incentivize patients with a gift card for completed evaluations and vouchers. Collect forms from patients at the check-out station.

### Step 14: Healthy Meals

### Volunteers and some patients will be at your See, Test & Treat program site anywhere between 3 to 8 hours whether receiving screenings, participating in the health fair or waiting for results. Providing a healthy breakfast, lunch or snack provides the opportunity to introduce patients to nutritious and healthy food options along with fueling your volunteer team.

### Consider the following:

### Approach local restaurants and grocery stores to donate food for the program

### Setting up a table in a main area with a volunteer assigned to manage the food station.

### Offering pre-packaged, grab and go food choices; provide culturally appropriate food based on the patient population being served

### Conducting a lunch and learn session

### Having a separate food area for volunteers

### Step 15: Addressing Barriers to Care

### See, Test & Treat recognizes that medically underserved women face several barriers to accessing health care, including transportation, lack of childcare, and being unaware of resources available to them.  While planning your program, consider addressing some of these barriers by offering:

### Children’s Activities:

### One barrier to care faced by women is the availability of childcare. When planning your program consider a space and process for offering children’s activities during the program. These can include coloring books, crafts, games, reading materials along with other activities.

### Consider the following:

### Offering age-appropriate activities, such as coloring, crafts, a balloon artist, and games

### Establishing an identification/matching system for each child/parent

### Determining the age range/limit for participation

### Securing volunteers who have experience working with children

### Checking with your Risk/Compliance department for guidance

### Assigning one volunteer per patient and child to sit and color with the child in the waiting room  while the patient is at their appointment

### Transportation:

### Many women lack access to transportation or the ability to pay for transportation to get to their doctor’s appointments. Consider assisting your target population by:

### Providing gift cards for Uber or Lyft

### Providing tokens for your local public transportation system

### Waiving the parking fee at your hospital’s parking lot

### Providing a shuttle for your patients

### Lack of Awareness Regarding Local Resources Available:

### Due to several factors many medically underserved women are unaware of local resources available to them to support their health. In addition to health education efforts mentioned in Step 13, also consider inviting patient navigators and local FQHCs to your health fair in order to help your patients enroll in programs that will allow them to establish a primary medical home.

### Step 16: Laboratory, Laboratory Personnel and Specimen Management

  - Space and personnel must meet all state/local requirements to screen for and diagnose cervical and breast cancer on the same day.

  - Ensure program has licensed/certified personnel to conduct all exams, obtain and process Pap specimens, and take and review breast images.

  - Follow the rules governing your organization regarding credentialing for personnel.

  - Ensure your program utilizes a CLIA-certified laboratory to perform specimen testing.

  - Determine the laboratory setup that works best while remaining compliant with state and federal regulations.

### Specimen Management

  - Establish a protocol for specimen labeling.

  - Identify a system to process specimens in the order in which they were collected.

  - Establish a protocol for batching and delivering specimens to the appropriate staff for processing and interpretation.

  - Avoid excessive batching of specimens, as that may result in processing delays that can impact the delivery of results to patients.

  - Arrange for volunteer couriers, if necessary.

### Step 17: Deliver Patient Results (See See, Test & Treat Toolkit)

  - Determine how the results will be collected and provided to the clinician, and who will be communicating these results to the patient.

  - Identify a private setting for delivery of same day Pap and Screening Mammogram results.

  - Identify protocols if patient expresses need to go home before they receive their results.

  - Explain abnormal results and further testing or procedures required. Avoid using the word “cancer.”

  - Triage patients to receive any further required testing available that day.

  - Provide a take-away card with contact information so patients can call post-program with any questions.

  - For further testing or treatment that is not available that day, connect patient with hospital or clinic personnel who can arrange and communicate next steps to patient (provide a take-away sheet with contact information).

### Step 18: Follow-up Testing and Treatment

In instances where abnormal findings are discovered through pelvic or Clinical breast exam, Pap test, or Screening Mammogram, host site clinicians are encouraged to provide patients with additional onsite treatment whenever feasible.

- When abnormal Pap test results are found, clinicians may find the following same-day procedures  beneficial to the patient:

    - Colposcopy

    - LEEP

- When abnormal breast results are found via Screening Mammogram or manual palpation:

- Additional mammogram views and/or

- Fine Needle Aspiration (FNA), often performed by a Cytopathologist.

- In cases where further treatment is needed that cannot be performed onsite, program hosts/clinicians are required to:

- Arrange follow-up, including locations, providers and financial arrangements for women with abnormal results requiring further care (provide a take-away sheet with contact information).

- Explain the follow-up plan to patients both orally and in writing before they leave the See, Test & Treat program.

- Provide patients with a card listing resources and contact information if they have any questions after leaving the See, Test & Treat event.

### Models for Follow-Up Care

See, Test & Treat host sites have employed various methods for connecting patients with abnormal Pap and Screening Mammogram results to further care. Tactics used include:

- Hospital affiliates committing to patient follow-up for cervical and breast abnormalities.

- Partner practice committing to patient follow-up for Pap and Screening Mammogram abnormalities.

- Triage with patient navigators and physicians working in area clinics/imaging centers that have committed to patient follow- up for cervical and breast abnormalities.

- Volunteer physicians accepting patients into their private practice.

- Referral to County medical center.

- Enrolling patients in a state/federally funded women’s cancer screening program, applying for Medicaid, or in a health insurance marketplace plan.

### Step 19: Debrief and Celebrate

### After your See, Test & Treat program it’s important to conduct a debrief session within a week of your event with CAP Foundation staff, all supporting staff and volunteers. The purpose is to gain input, determine what worked well and if any changes need to be made to your program for next year

### Celebrate your success! Host a thank you lunch the week after the event and invite the Hospital Administrators, C-Suite, and Volunteers.

### Recognize volunteers internally on message boards, flat screens, newsletters, intranet, institution website, press releases, etc.

### Leverage internal awards available within your institution for See, Test & Treat volunteers

### Consider sending out handwritten thank you notes.

### Step 20: Complete and Report Patient Outcomes and Patient Survey Results

- Within 30 days post program, submit your one month outcomes data and a budget reconciliation form (with supporting documents) via Survey Monkey Apply in order to receive the balance of your CAP Foundation grant.

- With 90 days post program submit your 3 month outcomes data and within 120 days submit your 6 month outcomes data.

These reports ensure that CAP Foundation staff is kept up to date on the outcomes of any patients that needed additional diagnostics or treatment. We ideally would like to follow the patients until they are connected with the information they need.

- After one year, look through medical records to see the number of See, Test & Treat patients that have visited your institution since attending See, Test &Treat, which is an indicator for the program’s success in connecting the patients to a medical home. Please submit this information through the data outcomes form provided to you by the CAP Foundation.

Rider
The CAP member pathologists are not employees, agents or representatives of the CAP Foundation, and have no affiliation with the CAP Foundation other than the CAP member pathologists’ professional membership with the College of American Pathologists. The CAP Foundation is not responsible for the actions or inactions of the CAP member pathologists. The participating sites and clinicians are at all times solely responsible for their own conduct, and should not rely on these Standard Operating Procedures in determining whether they have complied with their applicable professional standards of care.
APPENDIX 1 - ALLOWABLE COSTS FOR SEE, TEST & TREAT FUNDING

The CAP Foundation offers competitive grants of up to $20,000 to support See, Test & Treat program expenses that other grants and in-kind donations do not cover. The following table provides a description of program expenses that are allowable in your proposed See, Test & Treat budget:

| Type of Expense | Description |
| --- | --- |
| Medical Equipment | Costs associated with transport or rental of equipment to perform screening mammography, Pap test processing or other cervical or breast diagnostics procedures. |
| Testing Supplies | Testing supplies needed to perform the following screenings/diagnostic procedures during your See, Test & Treat program: Pelvic exam, Pap testing, colposcopy, LEEP, Clinical Breast Exam, screening Mammogram, Fine Needle Aspiration. NOTE: The cost to perform the test is not eligible for grant funding and should not be included in your See, Test & Treat budget. This funding may be reduced if an in-kind donation of any supplies is received. |
| Project Coordinator | An individual who will assist in planning/organizing all program logistics. Consider reaching out to a part-time staff person or a retired clinician who may be interested in taking on a temporary assignment; those in administrative fellowships or graduate students may value the experience in serving as a program coordinator. |
| Support Personnel | Hourly personnel who cannot volunteer their time to perform their normal job in support of the See, Test & Treat program. Examples of non-exempt staff include registration staff, specimen prep techs, hourly lab techs, radiology techs, housekeeping, etc. It is expected that exempt staff volunteer their time in support of the planning and execution of See, Test & Treat. Institution to follow their labor laws/ policy/ procedures specific to compensation of hourly staff supporting a humanitarian program providing a service/benefit to the community. |
| Marketing and Promotion | Expenses related to marketing and promoting your See, Test & Treat event to a target audience of medically underserved women residing in the community which the institution normally services. |
| Translation/Interpretation | Expenses associated with translation of educational and promotional materials or interpreters on the day of the event |
| Transportation | Funding support for the transportation of women to and from your See, Test & Treat event. |
| Children’s activities | Funding support for the purchase of supplies to support the children's activities that will be taking place at your See, Test & Treat program. Examples include games, coloring books, Legos/building block sets, stickers, art supplies, books, etc. |
| Meals | Healthy meal and snack options for both patients (and their families) attending and volunteers supporting your See, Test & Treat program. |
| Other | Other supplies and services needed to support your See, Test & Treat program (Office supplies, cleaning services, security, etc., ). Patient giveaways (except for gift cards, which are not fundable) are allowable expenses. |

APPENDIX 2 – SAMPLE PATIENT FLOW CHARTS

# APPENDIX 3: Guide for Determining Volunteer Need

| # Category (Personnel) | # Number of Suggested Volunteers |  | # Notes |
| --- | --- | --- | --- |
|  | # Screening 50 Women | # Screening 100 Women |  |
| # Patient On-Site Registration (Check In / Out) | # 4 | # 4 |  |
| # Patient Navigators | # 3 | # 6 |  |
| # Patient Greeters | # 5 | # 10 |  |
| # Staff Project Manager | # 1 | # 1 |  |
| # On-Site Coordinator | # 1 | # 1 |  |
| # Children’s Activity Coordinator | # 1 to 2 | # 1 to 2 | # Based on need |
| # Food Coordinator | # 1 | # 1 |  |
| # Supply Coordinator | # 1 | # 1 |  |
| # Cytotechnologist and Cyto Prep Tech | # 4 | # 6 |  |
| # Cytopathologist | # 2 | # 2 |  |
| # Pathologist | # 2 | # 2 |  |
| # Pathology Residents | # 6 | # 6 | # Assist with education; engage patients in viewing healthy and unhealthy cells via two-headed microscope |
| # Specimen Runners/Couriers | # 2 | # 3 |  |
| # Pathology/Laboratory Volunteers | # 3 | # 6 |  |
| # OB/GYN Administration | # 4 | # 6 |  |
| # OB/GYN | # 6 attending physicians | # 10 attending physicians | # Perform exams and provide patient results |
| # OB/GYN Residents | # 6 | # 6 | # Assist with patient prep/exam; taking patient history |
| # Nurse (NA/RN/MA) | # 6 | # 10 |  |
| # Colposcopy/LEEP (Provider) | # TBD | # TBD | # Based on need |
| # Colposcopy/LEEP (Nurse) | # TBD | # TBD | # Based on need |
| # Mammography Registration | # 1 | # 3 |  |
| # Radiologist | # 1 | # 1 |  |
| # Radiology Technician | # 2 | # 3 |  |
| # Phlebotomist | # 1 | # 1 |  |
| # Financial Aid | # 2 | # 3 |  |
| # Insurance Navigators | # 1 to 2 | # 1 to 2 |  |
| # Education | # TBD | # TBD | # Based on education offered |
| # Interpreters | # TBD | # TBD | # Based on need |
| # Total | # 58 | # 82 |  |