CAP Foundation See, Test & Treat Program Media Relations Timeline

| Month |  | Activity |  | Status |  |
| --- | --- | --- | --- | --- | --- |
| 5 months pre-event |  | Identify/Secure Photographer |  | Communicate as host action item on monthly conference calls |  |
|  |  | Explore broadcast opportunities in regional and local markets |  | Communicate as host action item on monthly conference calls |  |
|  |  | Contact regional ethnic media and public health outlets about possible placements |  | Communicate as host action item on monthly conference calls |  |
|  |  | Develop press materials: - Team contact list – host, CAP - Pitch letter - Multimedia press release - Fact sheet - Talking points - Media alert (to be distributed 3 weeks prior to the event, as well as the day before and day of event.) |  |  |  |
|  |  | Compile media list |  |  |  |
| 4 months pre-event |  | Continue to develop/finalize press materials CAP and Host Site Communications |  |  |  |
| 3 months pre-event |  | Distribute pitch letter and press release to long-lead publications and calendar of events editors |  |  |  |
|  |  | Make follow-up calls to the long-lead publications |  |  |  |
| 2 months pre-event |  | Continue to follow-up with the long-lead publications |  |  |  |
| 1-month pre-event |  | Explore possible pathologist interviews to record, distribute local radio stations. |  |  |  |
|  |  | Distribute press release to: - Local newspapers - Television stations - Radio stations - Social media outlets (e.g. CAP or host web sites, Twitter accounts, etc.) |  |  |  |
|  |  | Make follow-up calls to the media outlets which received the press release |  |  |  |
| 2 weeks pre-event |  | If produced, ensure pre-recorded radio interviews with pathologist are distributed to local radio stations |  |  |  |
|  |  | Distribute media alert to local television stations. Offer to do an on-air interview to educate the community about the importance of cancer screenings. |  |  |  |
|  |  | Continue to follow-up with local media outlets to see if planning to attend or cover the event. |  |  |  |
|  |  | Issue tweets, social media postings |  |  |  |
| Month | Activity |  | Status |  |
| Day Prior | Re-distribute media alert. Continue to follow-up with local media |  |  |  |
| EVENT DAY | Conduct media interviews with outlets that attend the event. |  |  |  |
|  | As budget or resources permit, select two photos to distribute via AP Photo Express. Develop captions |  |  |  |
|  | Engage social media from event: “tweets;” CAP and host Facebook postings; event photos |  |  |  |
| 1 – 2 weeks following | Media follow-up; results reporting |  |  |  |